NYX CORE

90-Day High-Priority Remediation Plan

From Solo Prototype to Enterprise-Ready Platform

Role: Interim CTO Engineering Directive

Date: April 12, 2026

Classification: INTERNAL — Engineering Sprint Plan

Post-Audit Remediation (Audit Date: April 12, 2026)

# Table of Contents

The following document contains six major sections plus a prioritized sprint backlog and investment readiness criteria.

- Executive Directive

- Section 1: Week 1-2 — The Security & Isolation Sprint

- 1.1 Multi-Tenancy: Middleware-Based Query Filtering

- 1.2 Secrets Management: Purge and Vault Migration

- 1.3 Auth Enforcement: REQUIRE_AUTH Across All 503 Endpoints

- Section 2: Week 3-4 — The Mathematical Integrity Sprint

- 2.1 Float/Decimal Boundary Fix in smart_excel_parser.py

- 2.2 Circuit-Breaker Pattern for the 7-Stage Pipeline

- Section 3: Month 2 — Codebase Consolidation & DevOps

- 3.1 Orchestration Framework Cleanup

- 3.2 Test Organization & CI/CD Pipeline

- Section 4: Month 3 — Enterprise Scale-Out

- 4.1 Adapter Standardization: The ERP Adapter Template

- 4.2 Bus Factor Mitigation: Technical Onboarding Guide

- Section 5: Prioritized Sprint Backlog (34 tickets, 258 hours)

- Section 6: Definition of Done — Axel Investment Readiness

# Executive Directive

As Interim CTO, I am issuing this directive following the April 12, 2026 Technical Due Diligence audit. The audit confirmed that NYX Core's technical foundation is genuine — the hybrid symbolic-neural architecture, deterministic Decimal pipeline, and 710+ entity knowledge graph represent real, defensible intellectual property. However, three critical blockers prevent any investment closing or enterprise deployment: (1) hardcoded secrets and disabled authentication across 503 endpoints, (2) zero multi-tenant data isolation — any customer can see every other customer's data, and (3) a Bus Factor of 1 with three competing orchestration frameworks that only the founder understands. This plan converts these red flags into resolved engineering tickets across 12 weeks of focused sprints. Every task has a Definition of Done, a code pattern, and an owner slot. The goal: by Week 12, NYX Core passes a repeat technical audit with zero Critical findings.

# Section 1: Week 1-2 — The Security & Isolation Sprint

## 1.1 Multi-Tenancy: Middleware-Based Query Filtering

### Problem Statement

Currently, database queries like select(CustomTool).order_by(CustomTool.created_at.desc()) in app/routers/tools.py line 34 return ALL records across all companies. The company field on Dataset exists for labeling, not access control. There is no middleware injecting company_id filters into SQLAlchemy queries.

### Design Pattern: Tenant Context Middleware

The solution uses a three-layer approach: (a) a TenantContext that extracts tenant_id from the authenticated JWT token, (b) a SQLAlchemy event listener that automatically appends WHERE company_id = :tenant_id to every query, and (c) a decorator for router endpoints that validates tenant access.

### Code Pattern — TenantContext

Create as app/middleware/tenant.py:

"""Multi-tenant query isolation middleware.""" from contextvars import ContextVar from typing import Optional from starlette.middleware.base import BaseHTTPMiddleware from starlette.requests import Request # Thread-safe tenant context _tenant_id: ContextVar[Optional[int]] = ContextVar("tenant_id", default=None) def get_current_tenant() -> Optional[int]: return _tenant_id.get() class TenantMiddleware(BaseHTTPMiddleware): """Extract tenant_id from JWT and set in context for every request.""" EXEMPT_PATHS = {"/health", "/api/auth/login", "/api/auth/register", "/docs", "/metrics"} async def dispatch(self, request: Request, call_next): if any(request.url.path.startswith(p) for p in self.EXEMPT_PATHS): return await call_next(request) user = getattr(request.state, "user", None) if user and hasattr(user, "company_id"): token = _tenant_id.set(user.company_id) try: response = await call_next(request) finally: _tenant_id.reset(token) return response return await call_next(request)

### Code Pattern — SQLAlchemy Query Filter

Add to app/database.py:

from sqlalchemy import event from app.middleware.tenant import get_current_tenant TENANT_MODELS = {"CustomTool", "Dataset", "FinancialDocument", "Transaction", "JournalEntry", "Alert", "RevenueItem", "COGSItem"} @event.listens_for(Session, "do_orm_execute") def _inject_tenant_filter(orm_execute_state): """Automatically append company_id filter to all tenant-scoped queries.""" tenant_id = get_current_tenant() if tenant_id is None: return if orm_execute_state.is_select: mapper = orm_execute_state.bind_arguments.get("mapper") if mapper and mapper.class_.__name__ in TENANT_MODELS: orm_execute_state.statement = orm_execute_state.statement.filter_by( company_id=tenant_id )

### Code Pattern — Router Decorator

Add to app/auth.py:

from functools import wraps from app.middleware.tenant import get_current_tenant def require_tenant(f): """Decorator ensuring tenant context is set before endpoint executes.""" @wraps(f) async def wrapper(*args, **kwargs): if get_current_tenant() is None: raise HTTPException(403, "Tenant context required. Authenticate first.") return await f(*args, **kwargs) return wrapper

### Implementation Steps

- Add company_id column to all models in TENANT_MODELS that lack it (estimated: 4 models need migration).

- Create Alembic migration to backfill company_id for existing records.

- Register TenantMiddleware in main.py AFTER AuthMiddleware (order matters).

- Add the SQLAlchemy event listener to database.py.

- Write integration test: create 2 tenants, insert data for each, verify cross-tenant queries return zero results.

Definition of Done: Integration test proves that Tenant A cannot see Tenant B's datasets, tools, documents, transactions, or journal entries under any API endpoint.

## 1.2 Secrets Management: Purge and Vault Migration

### Problem Statement

The committed .env file contains production NVIDIA API keys (nvapi-ICp5...), a Vercel deployment token (vcp_0z8mg...), and the JWT SECRET_KEY (2d8f921a...). These credentials are in git history and must be considered compromised.

### Immediate Actions (Day 1)

### Action 1 — Rotate All Keys

- NVIDIA: Generate new API key at build.nvidia.com dashboard. Revoke old key nvapi-ICp5uQ6F... immediately.

- Vercel: Regenerate token in Vercel dashboard under Settings > Tokens. Revoke vcp_0z8mg1sN...

- JWT SECRET_KEY: Generate new 64-char hex key using: python -c "import secrets; print(secrets.token_hex(32))"

- Any other API keys referenced in .env (Anthropic, Google, etc.).

### Action 2 — Purge Git History

# Install git-filter-repo (preferred over filter-branch) pip install git-filter-repo # Remove .env and .env.local from ALL history git filter-repo --invert-paths --path .env --path .env.local --force # Force-push to all remotes git push origin --force --all git push origin --force --tags

### Action 3 — Prevent Recurrence

# Add to .gitignore (verify these are present) .env .env.local .env.production *.key *.pem

### Vault Migration Plan

For Development: Use .env.example with placeholder values only. Each developer creates their own .env locally (never committed).

For Production (Docker/Cloud):

- Option A — Docker Secrets: Mount secrets as files in docker-compose.yml using the secrets directive. Reference via /run/secrets/nvidia_api_key in config.py.

- Option B — Cloud Secret Manager: For GCP deployment, use Google Secret Manager. For AWS, use AWS Secrets Manager. Access via SDK at startup in config.py lifespan handler.

### Config.py Modification Pattern

import os from pathlib import Path def _read_secret(name: str, fallback_env: str = "") -> str: """Read from Docker secret file first, fall back to env var.""" secret_path = Path(f"/run/secrets/{name}") if secret_path.exists(): return secret_path.read_text().strip() return os.getenv(fallback_env or name.upper(), "") class Settings: NVIDIA_API_KEY: str = _read_secret("nvidia_api_key", "NVIDIA_API_KEY") SECRET_KEY: str = _read_secret("jwt_secret_key", "SECRET_KEY") VERCEL_TOKEN: str = _read_secret("vercel_token", "VERCEL_TOKEN")

Definition of Done: (a) git log --all --full-history -- .env returns zero commits, (b) all rotated keys are verified working in staging, (c) .gitignore blocks all secret file patterns, (d) production deployment reads secrets from vault/mounted files, not environment variables in plaintext.

## 1.3 Auth Enforcement: REQUIRE_AUTH Across All 503 Endpoints

### Problem Statement

The .env file has REQUIRE_AUTH=false. The auth middleware (app/middleware/auth_middleware.py) respects this flag, meaning all endpoints are publicly accessible. Many router endpoints use get_optional_user instead of get_current_user, allowing unauthenticated access even when auth is enabled.

### Implementation Plan

### Step 1 — Force REQUIRE_AUTH=true as Default

In app/config.py, change the default:

# BEFORE (dangerous default) REQUIRE_AUTH: bool = False # AFTER (secure default) REQUIRE_AUTH: bool = True # Override with env var only in local dev

### Step 2 — Audit All get_optional_user Usages

Every endpoint using Depends(get_optional_user) must be reviewed. The rule: if the endpoint reads or writes tenant data, it MUST use get_current_user (which raises 401 if no token). Reserve get_optional_user only for truly public endpoints (health check, public config, docs).

Endpoints to convert (found in audit):

- documents_router.py line 55: change to get_current_user

- tools.py: add Depends(get_current_user) to all 6 endpoints

- Multiple endpoints in datasets.py, analytics.py, journal_router.py

### Step 3 — Add Endpoint Auth Coverage Test

# tests/test_auth_coverage.py import pytest from httpx import AsyncClient from main import app EXEMPT_PATHS = ["/health", "/api/auth/login", "/api/auth/register", "/docs", "/openapi.json"] @pytest.mark.asyncio async def test_all_endpoints_require_auth(): """Every non-exempt endpoint must return 401 without a token.""" async with AsyncClient(app=app, base_url="http://test") as client: for route in app.routes: if hasattr(route, "path") and route.path not in EXEMPT_PATHS: response = await client.get(route.path) assert response.status_code in (401, 405, 307), ( f"SECURITY: {route.path} returned {response.status_code} without auth" )

Definition of Done: (a) REQUIRE_AUTH defaults to True in code, (b) test_auth_coverage passes with zero unauthenticated non-exempt endpoints, (c) staging deployment tested with auth enabled — all frontend flows work with JWT tokens.

# Section 2: Week 3-4 — The Mathematical Integrity Sprint

## 2.1 Float/Decimal Boundary Fix in smart_excel_parser.py

### Problem Statement

The _get() helper at line 330 of smart_excel_parser.py casts all values to float before arithmetic. The compute_derived_metrics() function (lines 320-385) then performs float arithmetic (revenue - cogs, ebitda / revenue * 100) and uses Python's built-in round() instead of Decimal with ROUND_HALF_UP. This introduces potential 0.01% rounding errors at the ingestion boundary — before data enters the protected Decimal pipeline.

### The Fix — Replace float with Decimal Throughout

# app/services/smart_excel_parser.py from decimal import Decimal, ROUND_HALF_UP, InvalidOperation _TWO_PLACES = Decimal("0.01") _ZERO = Decimal("0") def _safe_decimal(v) -> Optional[Decimal]: """Convert any value to Decimal safely. Returns None on failure.""" if v is None: return None try: if isinstance(v, Decimal): return v if isinstance(v, float): return Decimal(str(v)) return Decimal(str(v)) except (InvalidOperation, ValueError, TypeError): return None def compute_derived_metrics(data: Dict[str, Any]) -> Tuple[Dict[str, Any], List[str]]: """Compute missing derived metrics using ONLY Decimal arithmetic.""" d = dict(data) corrections = [] def _get(key: str) -> Optional[Decimal]: return _safe_decimal(d.get(key)) revenue = _get("revenue") cogs = _get("cogs") gross_profit = _get("gross_profit") if gross_profit is None and revenue is not None and cogs is not None: gross_profit = revenue - cogs d["gross_profit"] = gross_profit corrections.append("Computed gross_profit = revenue - cogs") if revenue and revenue != _ZERO: if _get("gross_margin_pct") is None and gross_profit is not None: d["gross_margin_pct"] = (gross_profit / revenue * 100).quantize( _TWO_PLACES, rounding=ROUND_HALF_UP) corrections.append("Computed gross_margin_pct") return d, corrections

### Regression Test

# tests/test_decimal_boundary.py from decimal import Decimal from app.services.smart_excel_parser import compute_derived_metrics def test_no_float_in_derived_metrics(): """Every output value must be Decimal, never float.""" data = {"revenue": "51163022.93", "cogs": "44572371.58"} result, corrections = compute_derived_metrics(data) for key, value in result.items(): if isinstance(value, (int, str)): continue assert isinstance(value, Decimal), f"{key} is {type(value)}, expected Decimal" assert result["gross_profit"] == Decimal("6590651.35") assert result["gross_margin_pct"] == Decimal("12.88") def test_float_input_converted_safely(): """Float inputs (from Excel) must be converted via string repr.""" data = {"revenue": 51163022.93, "cogs": 44572371.58} result, _ = compute_derived_metrics(data) assert isinstance(result["gross_profit"], Decimal)

Definition of Done: (a) compute_derived_metrics returns only Decimal values for all financial fields, (b) test_decimal_boundary passes, (c) no float() calls remain in any financial computation path.

## 2.2 Circuit-Breaker Pattern for the 7-Stage Pipeline

### Problem Statement

In app/orchestrator/orchestrator_v3.py, every stage is wrapped in try/except with a catch-all that sets the result to None/empty and continues. When Stage 3 (Reconstruction) fails or the Constraint Graph flags a CRITICAL violation (BS equation or TB balance), the pipeline continues to Stage 6 (LLM Reasoning) and Stage 7 (Monitoring) using degraded data. This produces narratives and alerts based on incomplete or invalid financial data — a dangerous outcome for a financial intelligence product.

### Design: PipelineCircuitBreaker

# app/orchestrator/circuit_breaker.py from dataclasses import dataclass, field from enum import Enum from typing import List, Optional class BreakerState(Enum): CLOSED = "closed" OPEN = "open" HALF_OPEN = "half_open" class HaltReason(Enum): GAAP_VIOLATION = "critical_gaap_violation" RECONSTRUCTION_FAILED = "reconstruction_failed" CALCULATION_FAILED = "calculation_failed" DATA_INTEGRITY = "data_integrity_failure" @dataclass class CircuitBreaker: state: BreakerState = BreakerState.CLOSED halt_reasons: List[str] = field(default_factory=list) critical_failures: int = 0 warning_count: int = 0 MAX_CRITICAL: int = 1 MAX_WARNINGS: int = 3 def record_critical(self, reason: HaltReason, detail: str = ""): """Record a critical failure. Opens the breaker immediately.""" self.critical_failures += 1 self.halt_reasons.append(f"CRITICAL: {reason.value} — {detail}") self.state = BreakerState.OPEN def record_warning(self, detail: str = ""): """Record a warning. Degrades to HALF_OPEN after threshold.""" self.warning_count += 1 self.halt_reasons.append(f"WARNING: {detail}") if self.warning_count >= self.MAX_WARNINGS: self.state = BreakerState.HALF_OPEN def should_continue(self) -> bool: """Can the pipeline proceed to the next stage?""" return self.state != BreakerState.OPEN def is_degraded(self) -> bool: """Should LLM narratives be marked as provisional?""" return self.state == BreakerState.HALF_OPEN

Definition of Done: (a) Upload a file with deliberately unbalanced BS — pipeline halts after Stage 3 with action_required message, (b) Upload a file with minor NI inconsistency — pipeline continues but LLM output marked provisional, (c) Upload a clean file — pipeline runs all 7 stages normally.

# Section 3: Month 2 — Codebase Consolidation & DevOps

## 3.1 Orchestration Framework Cleanup

### Problem Statement

The audit found three competing orchestration frameworks:

- Framework 1 — OrchestratorV3 (app/orchestrator/orchestrator_v3.py): Procedural Python, 369 lines. Runs 7 stages sequentially with try/except per stage.

- Framework 2 — LangGraph Pipeline (app/graph/graph.py + nodes.py + state.py): LangGraph StateGraph with 10 nodes, conditional routing. 926 lines total.

- Framework 3 — Custom StateGraph (app/orchestration/state_graph.py + compiled_graph.py + chat_graph.py): LangGraph-compatible custom implementation, 958 lines.

### Recommendation: KEEP LangGraph (Framework 2)

Rationale:

- LangGraph is an industry-standard library with community support, documentation, and upgrade path.

- The 10-node graph (vs 7-stage procedural) already includes anomaly detection, what-if simulation, and report generation — more complete.

- Conditional routing is architecturally superior to procedural if-checks.

- State management via TypedDict (FinAIState) provides type safety.

### Refactoring Strategy

- Phase 1 (Week 5): Port the circuit-breaker pattern from Section 2.2 into the LangGraph nodes.

- Phase 2 (Week 6): Migrate any unique logic from OrchestratorV3 that is missing in LangGraph nodes.

- Phase 3 (Week 7): Delete deprecated code. Remove app/orchestrator/orchestrator_v3.py entirely.

- Phase 4 (Week 8): Rename app/graph/ to app/pipeline/ for clarity.

Definition of Done: grep -rn "orchestrator_v3|OrchestratorV3" app/ returns zero results. Only one graph builder function exists. All tests pass.

## 3.2 Test Organization & CI/CD Pipeline

### Problem Statement

22 ad-hoc test files exist at the project root alongside 19 structured tests in tests/. No CI/CD pipeline exists — deployment is manual.

### Test Reorganization Plan

Target directory structure:

tests/ conftest.py (already exists — shared fixtures) unit/ test_decimal_boundary.py (new) test_circuit_breaker.py (new) test_tenant_isolation.py (new) test_auth_coverage.py (new) test_decimal.py test_financial_correctness.py integration/ test_orchestrator.py test_prediction_loop.py test_gl_pipeline.py test_full_pipeline.py security/ test_security.py test_secrets_not_committed.py (new) e2e/ test_api.py test_e2e.py

Step 1 (Week 5): Create directory structure. Move existing tests. Delete root-level duplicates.

Step 2 (Week 6): Write the 4 new test files from Sections 1 and 2.

Step 3 (Week 6): Configure pytest.ini with markers: unit, integration, security, e2e.

### GitHub Actions CI/CD Pipeline

# .github/workflows/ci.yml name: NYX Core CI on: push: branches: [main, develop] pull_request: branches: [main] jobs: security-check: runs-on: ubuntu-latest steps: - uses: actions/checkout@v4 - name: Check for secrets in code run: ¦ if git ls-files ¦ grep -E '\.env$¦\.env\.local$'; then echo "FATAL: .env files found in repository" exit 1 fi if grep -rn "nvapi-\¦vcp_\¦sk-ant-" app/ --include="*.py"; then echo "FATAL: Hardcoded API keys detected" exit 1 fi unit-tests: runs-on: ubuntu-latest needs: security-check steps: - uses: actions/checkout@v4 - uses: actions/setup-python@v5 with: python-version: "3.12" - run: pip install -r requirements.txt - run: pytest tests/unit/ -v --tb=short -x integration-tests: runs-on: ubuntu-latest needs: unit-tests services: postgres: image: postgres:16 env: POSTGRES_PASSWORD: test POSTGRES_DB: finai_test ports: - 5432:5432 steps: - uses: actions/checkout@v4 - uses: actions/setup-python@v5 with: python-version: "3.12" - run: pip install -r requirements.txt - run: pytest tests/integration/ -v --tb=short env: DATABASE_URL: postgresql+asyncpg://postgres:test@localhost/finai_test

Definition of Done: (a) Zero test files at project root, (b) pytest tests/ runs all tests in proper hierarchy, (c) GitHub Actions passes on every push to main, (d) PRs cannot merge without green CI.

# Section 4: Month 3 — Enterprise Scale-Out

## 4.1 Adapter Standardization: The ERP Adapter Template

### Problem Statement

The 1C Interpreter (app/services/onec_interpreter.py, 2000+ lines) is excellent but bespoke. To deliver on the "2-week industry adapter" promise, the adapter pattern must be standardized into a template that a new engineer can implement without understanding the full codebase.

### Adapter Interface Design

# app/adapters/base_adapter.py from abc import ABC, abstractmethod from dataclasses import dataclass from decimal import Decimal from typing import Dict, List, Optional from pathlib import Path @dataclass class StandardAccount: """Normalized account representation.""" code: str name_primary: str name_secondary: str = "" account_type: str = "" normal_balance: str = "" ifrs_section: str = "" ifrs_line: str = "" bs_side: str = "" parent_code: Optional[str] = None is_group: bool = False balance: Optional[Decimal] = None @dataclass class StandardTransaction: """Normalized transaction.""" date: str debit_account: str credit_account: str amount: Decimal description: str = "" document_ref: str = "" currency: str = "GEL" class BaseERPAdapter(ABC): """Template for ERP system adapters.""" @property @abstractmethod def system_name(self) -> str: """e.g. '1c', 'quickbooks', 'sap_b1'""" @property @abstractmethod def supported_formats(self) -> List[str]: """File extensions this adapter can parse""" @abstractmethod def detect(self, file_path: Path) -> float: """Return confidence 0.0-1.0 that this file is from this ERP system.""" @abstractmethod def parse_chart_of_accounts(self, file_path: Path) -> List[StandardAccount]: """Parse a COA export into StandardAccount list.""" @abstractmethod def parse_transactions(self, file_path: Path) -> List[StandardTransaction]: """Parse a transaction export into StandardTransaction list.""" @abstractmethod def map_to_ifrs(self, account: StandardAccount) -> StandardAccount: """Apply IFRS classification rules specific to this ERP system."""

Migration Path for Existing 1C Interpreter:

- Week 9: Refactor onec_interpreter.py to implement BaseERPAdapter.

- Week 10: Implement QuickBooks adapter as proof of template.

- Week 11: Document the adapter creation process.

Definition of Done: (a) OneCAdapter passes all existing 1C tests via the new interface, (b) QuickBooksAdapter can parse a sample QBO file, (c) detect_erp_system correctly auto-detects between 1C and QuickBooks files.

## 4.2 Bus Factor Mitigation: Technical Onboarding Guide

### Problem Statement

A Bus Factor of 1 means the project dies if the founder is unavailable. The codebase has 108+ Python files, 80+ services, three orchestration frameworks, Georgian-specific domain knowledge, and implicit conventions that exist only in the founder's head.

### Onboarding Document Structure (ONBOARDING.md)

Part 1 — Architecture Overview (Day 1):

  - System architecture diagram, pipeline flow

  - The ONE canonical pipeline: LangGraph graph in app/graph/graph.py

  - Data flow: Upload → SmartExcelParser → ConstraintGraph → LangGraph Pipeline → Output

  - Key design decisions: Why Decimal not float. Why symbolic validation before LLM.

Part 2 — Domain Knowledge (Day 2-3):

  - Georgian IFRS account structure (classes 1-9)

  - 1C accounting system: what it is, why it matters

  - The constraint graph's 6 GAAP rules and tolerance thresholds

  - Financial statement relationships: BS, IS, CF, TB cross-validation

Part 3 — Code Navigation Guide (Day 4-5):

  - "Change Excel parsing" → app/services/smart_excel_parser.py

  - "Add financial calculation" → app/services/calculation_engine.py (use Decimal)

  - "Modify pipeline" → app/graph/graph.py (add node), app/graph/nodes.py (implement)

  - "Add API endpoint" → app/routers/ (create router, register in main.py)

Part 4 — Local Development Setup (Day 1):

  - One-command setup: docker compose up -d

  - Run tests: pytest tests/unit/ -v

Part 5 — Architecture Decision Records (ADRs):

  - ADR-001: Why LangGraph over procedural orchestration

  - ADR-002: Why Python Decimal over float for financial math

  - ADR-003: Why symbolic constraint validation before LLM reasoning

  - ADR-004: Why SQLAlchemy event listener for multi-tenancy

  - ADR-005: Why template narratives as primary, LLM narratives as secondary

Part 6 — "What Not to Touch" List:

  - Constraint graph tolerance thresholds without consulting a CPA

  - 1C IFRS mapping table without consulting a Georgian accountant

  - LLM chain fallback order without load testing

  - Decimal pipeline — never introduce float arithmetic in financial calculations

Definition of Done: (a) ONBOARDING.md covers all 6 parts, (b) developer unfamiliar with codebase can set up local dev and make a simple change within 5 days, (c) 5 ADRs written and committed.

# Section 5: Prioritized Sprint Backlog

All 34 tickets with assignments, estimates, and dependencies:

| Ticket | Title | Sprint | Priority | Est | Depends | Status |
| --- | --- | --- | --- | --- | --- | --- |
| NYX-001 | Rotate all compromised API keys | W1 | P0-CRITICAL | 2h | None | TODO |
| NYX-002 | Purge .env from git history | W1 | P0-CRITICAL | 4h | NYX-001 | TODO |
| NYX-003 | Add .env to .gitignore | W1 | P0-CRITICAL | 1h | NYX-002 | TODO |
| NYX-004 | Docker secrets config pattern | W1 | P1-HIGH | 4h | NYX-003 | TODO |
| NYX-005 | Set REQUIRE_AUTH=true default | W1 | P0-CRITICAL | 1h | None | TODO |
| NYX-006 | Convert get_optional_user calls | W1 | P0-CRITICAL | 8h | NYX-005 | TODO |
| NYX-007 | Write test_auth_coverage.py | W1 | P0-CRITICAL | 4h | NYX-006 | TODO |
| NYX-008 | Create TenantMiddleware | W2 | P0-CRITICAL | 8h | NYX-005 | TODO |
| NYX-009 | Add SQLAlchemy tenant filter | W2 | P0-CRITICAL | 4h | NYX-008 | TODO |
| NYX-010 | Alembic migration: add company_id | W2 | P0-CRITICAL | 4h | NYX-008 | TODO |
| NYX-011 | Write test_tenant_isolation.py | W2 | P1-HIGH | 8h | NYX-009 | TODO |
| NYX-012 | Replace float with Decimal | W3 | P1-HIGH | 4h | None | TODO |
| NYX-013 | Write test_decimal_boundary.py | W3 | P1-HIGH | 4h | NYX-012 | TODO |
| NYX-014 | Implement CircuitBreaker class | W3 | P1-HIGH | 8h | None | TODO |
| NYX-015 | Integrate circuit breaker into V3 | W4 | P1-HIGH | 8h | NYX-014 | TODO |
| NYX-016 | Wire ConstraintGraph validation | W4 | P1-HIGH | 4h | NYX-015 | TODO |
| NYX-017 | Write test_circuit_breaker.py | W4 | P1-HIGH | 8h | NYX-016 | TODO |
| NYX-018 | Port circuit breaker to LangGraph | W5 | P2-MEDIUM | 8h | NYX-017 | TODO |
| NYX-019 | Migrate OrchestratorV3 logic | W6 | P2-MEDIUM | 16h | NYX-018 | TODO |
| NYX-020 | Delete OrchestratorV3 frameworks | W7 | P2-MEDIUM | 4h | NYX-019 | TODO |
| NYX-021 | Reorganize test files | W5 | P2-MEDIUM | 8h | None | TODO |
| NYX-022 | Configure pytest.ini markers | W5 | P2-MEDIUM | 2h | NYX-021 | TODO |
| NYX-023 | Create GitHub Actions CI pipeline | W6 | P1-HIGH | 8h | NYX-022 | TODO |
| NYX-024 | Add security-check job to CI | W6 | P1-HIGH | 4h | NYX-023 | TODO |
| NYX-025 | Create BaseERPAdapter class | W9 | P2-MEDIUM | 8h | None | TODO |
| NYX-026 | Refactor OneCInterpreter | W9 | P2-MEDIUM | 16h | NYX-025 | TODO |
| NYX-027 | Implement QuickBooksAdapter | W10 | P2-MEDIUM | 40h | NYX-025 | TODO |
| NYX-028 | Create ONBOARDING.md | W10 | P1-HIGH | 16h | NYX-020 | TODO |
| NYX-029 | Write 5 Architecture Decision Records | W11 | P2-MEDIUM | 8h | NYX-028 | TODO |
| NYX-030 | Register ConsolidationAgent | W7 | P3-LOW | 2h | None | TODO |
| NYX-031 | Fix DecisionAgent self-registration | W7 | P3-LOW | 4h | None | TODO |
| NYX-032 | Eliminate bare except: catches | W8 | P2-MEDIUM | 4h | None | TODO |
| NYX-033 | Add SourceMetadata enum | W8 | P2-MEDIUM | 8h | None | TODO |
| NYX-034 | Repeat technical audit | W12 | P0-CRITICAL | 16h | ALL | TODO |

Totals: 34 tickets, ~258 engineering hours, 12 weeks

# Section 6: Definition of Done — Axel Investment Readiness

The project is ready for Axel's final signature when ALL of the following conditions are met:

## Condition 1 — Zero Critical Security Findings

- No hardcoded secrets in git history (verified by automated scanner).

- REQUIRE_AUTH=true enforced, all endpoints return 401 without token.

- Multi-tenant isolation proven by cross-tenant integration test.

## Condition 2 — Financial Integrity Guarantee

- All financial arithmetic uses Python Decimal end-to-end (Excel parse to DB store).

- Circuit breaker halts pipeline on critical GAAP violations.

- Constraint graph validates BS equation, TB balance before any narrative generation.

## Condition 3 — Maintainable Codebase

- Single canonical orchestration framework (LangGraph).

- All tests in structured tests/ directory with CI/CD running on every commit.

- ONBOARDING.md enables a new engineer to contribute within 5 days.

- 5 Architecture Decision Records committed.

## Condition 4 — Enterprise Deployment Path

- BaseERPAdapter template proven with at least 2 adapters (1C + QuickBooks).

- Docker deployment stack passes health checks with auth enabled.

- Secrets managed via vault/mounted files, not environment variables.

## Condition 5 — Repeat Audit Score

- Technical audit score improves from 5.7/10 to 8.0/10 or higher.

- Zero CRITICAL findings. Maximum 2 MEDIUM findings (documented with mitigation plans).

- Security score improves from 4/10 to 8/10 or higher.

When these 5 conditions are met, the Interim CTO certifies the codebase as enterprise-ready and recommends proceeding with Axel's investment.